## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Shreya | 2026-09-01 | Incorrect file type handling when unsupported file extensions were uploaded. | Sprint 1 | Shreya | Logical | Added file extension validation in document_processor.py and restricted processing to PDF, DOCX, CSV and TXT files. | 2026-09-01 | Closed | Unsupported file types are now rejected with an appropriate message.
2 | Shreya | 2026-09-01 | PDF extraction did not handle some documents with empty or unreadable text correctly. | Sprint 1 | Shreya | Logical | Added validation after PDF text extraction and handled empty extraction cases. | 2026-09-01 | Closed | Valid text-based PDFs are processed successfully.
3 | Shreya | 2026-09-01 | CSV rows were initially difficult to retrieve semantically when stored only as raw tabular data. | Sprint 1 | Shreya | Maintainability | Converted CSV rows into structured semantic text such as `Task: Payment Gateway | 2026-09-01 | Closed | Status: blocked
4 | Shreya | 2026-09-01 | Retrieved RAG results could contain irrelevant project information for broad questions. | Sprint 1 | Shreya | Logical | Adjusted vector retrieval configuration and retrieval count to improve relevant context selection. | 2026-09-01 | Closed | Retrieval relevance improved during testing.
5 | Shreya | 2026-09-01 | Risk/blocker information was not directly identifiable from raw retrieved chunks. | Sprint 1 | Shreya | Logical | Added RAG-based analysis of retrieved project context to identify risk and blocker information. | 2026-09-01 | Closed | Risk and blocker information can now be identified from relevant project context.
6 | Shreya | 2026-09-10 | Gemini model gemini-2.5-flash returned 404 NOT_FOUND because the model was no longer available. | Sprint 2 | Shreya | Logical | Updated the Gemini model configuration to gemini-3.6-flash across the required project files. | 2026-09-10 | Closed | Deprecated model configuration was replaced.
7 | Shreya | 2026-09-10 | Google Cloud API key returned 403 PERMISSION_DENIED because the associated project was restricted. | Sprint 2 | Shreya | Configuration | Switched the application to Groq as the primary LLM provider and retained Gemini only as an optional fallback. | 2026-09-10 | Closed | Issue was related to the Google Cloud project configuration.
8 | Shreya | 2026-09-11 | Groq model llama-3.3-70b-versatile returned 404 because the model was no longer available. | Sprint 2 | Shreya | Configuration | Replaced the deprecated Groq model with openai/gpt-oss-120b in the relevant configuration and application files. | 2026-09-11 | Closed | Updated to a supported Groq model.
9 | Shreya | 2026-09-12 | Groq returned a JSON list while the Pydantic validation expected a dictionary. | Sprint 2 | Shreya | Logical | Added list-unwrapping logic to _parse_and_validate_json() in the Groq and Gemini providers. | 2026-09-12 | Closed | Structured output validation now handles the returned list format.
10 | Shreya | 2026-09-13 | Groq request timed out after 30 seconds when processing large document contexts. | Sprint 2 | Shreya | Performance | Increased AGENT_TIMEOUT_SECONDS from 30 to 60 seconds. | 2026-09-13 | Closed | Timeout configuration was adjusted for larger contexts.
11 | Shreya | 2026-09-14 | A redundant fallback information message was displayed in the Streamlit interface after Gemini failure. | Sprint 2 | Shreya | UI | Removed the unnecessary fallback message and configured Groq as the direct primary provider. | 2026-09-14 | Closed | UI no longer displays the unnecessary fallback notification.
12 | Shreya | 2026-09-15 | VS Code displayed a Cannot find module groq warning because the wrong Python interpreter was selected. | Sprint 2 | Shreya | Configuration | Selected .\venv\Scripts\python.exe as the VS Code Python interpreter. | 2026-09-15 | Closed | VS Code now uses the project virtual environment.
13 | Shreya | 2026-09-24 | User Story generation did not consistently preserve all available project scope and deliverable information. | Sprint 3 | Shreya | Logical | Updated the Documentation Generation Agent to use existing Scope Agent outputs and project evidence when generating User Stories. | 2026-09-24 | Closed | Generated User Stories are now based on available project scope and deliverables.
14 | Shreya | 2026-09-25 | Risk Register generation could include incomplete information when probability, owner or mitigation details were not available in the project documents. | Sprint 3 | Shreya | Logical | Added handling for unavailable fields and configured the generator to explicitly mark unsupported information instead of inventing values. | 2026-09-25 | Closed | Missing information is now identified instead of being generated without evidence.
15 | Shreya | 2026-09-25 | Action Item generation did not consistently retain source information from the existing Blocker Agent results. | Sprint 3 | Shreya | Logical | Added source/evidence fields to generated Action Items and reused the existing blocker information. | 2026-09-25 | Closed | Action Items can now be traced to available project evidence.
16 | Shreya | 2026-09-25 | Invalid or incomplete LLM output could cause structured documentation generation to fail. | Sprint 3 | Shreya | Logical | Added structured validation and error handling for User Story, Risk Register and Action Item outputs. | 2026-09-25 | Closed | Invalid generated data is handled without crashing the Streamlit application.
17 | Shreya | 2026-09-26 | Initial Project Health Score calculation required a deterministic method instead of relying on an LLM-generated score. | Sprint 3 | Shreya | Logical | Implemented deterministic scoring using scope clarity, timeline risk, blocker status and delivery risk indicators. | 2026-09-26 | Closed | Health Score is now calculated using defined project indicators.
18 | Shreya | 2026-09-27 | Overall health score alone did not clearly explain the factors affecting project health. | Sprint 3 | Shreya | UI | Added dimension-wise health scores and key factors contributing to the overall health score. | 2026-09-27 | Closed | Users can now view the individual health dimensions and contributing factors.
19 | Shreya | 2026-09-27 | Projects with insufficient information could receive a misleading health assessment. | Sprint 3 | Shreya | Logical | Added insufficient-data handling and confidence/data-sufficiency indicators for incomplete project information. | 2026-09-27 | Closed | The system now identifies when available project data is insufficient.
20 | Shreya | 2026-09-28 | Conversational Assistant needed to reuse the existing RAG pipeline instead of creating a separate retrieval mechanism. | Sprint 3 | Shreya | Architecture | Integrated the assistant with the existing ChromaDB retrieval, project filtering and RAG components. | 2026-09-28 | Closed | No separate document ingestion or vector database was introduced.
21 | Shreya | 2026-09-28 | Conversational responses could lack sufficient project context for questions involving risks, blockers and delivery status. | Sprint 3 | Shreya | Logical | Added relevant existing Risk, Blocker and Health outputs as additional context when answering project questions. | 2026-09-28 | Closed | Assistant responses now use project intelligence along with retrieved evidence where applicable.
22 | Shreya | 2026-09-29 | Follow-up questions containing references such as "them", "it" or "those risks" were not consistently understood without conversation context. | Sprint 3 | Shreya | Logical | Added limited conversation history to maintain context between related project questions. | 2026-09-29 | Closed | Follow-up questions can now use relevant previous conversation context.
23 | Shreya | 2026-09-29 | Assistant could not provide a reliable response when the requested information was not available in the uploaded project documents. | Sprint 3 | Shreya | Logical | Added insufficient-evidence handling so the assistant reports when supporting project information is unavailable instead of guessing. | 2026-09-29 | Closed | Unsupported project questions are now handled without generating unsupported information.
24 | Shreya | 2026-09-29 | Conversational Assistant required validation to ensure that information from one project was not retrieved for another project. | Sprint 3 | Shreya | Security | Tested and verified project_id filtering during conversational retrieval and project-level analysis. | 2026-09-29 | Closed | Project-specific retrieval remains isolated between projects.
25 | Shreya | 2026-09-29 | LLM/API failures during conversational queries could interrupt the user interaction. | Sprint 3 | Shreya | Error Handling | Added error handling for provider/API failures and displayed understandable messages in the Streamlit interface. | 2026-09-29 | Closed | LLM failures no longer cause the Streamlit application to crash.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others